## Sheet1
Story | Task | Estimate min (hr) | Estimate max (hr) | Actual | Comment
Backend
B-1 | Database Migration | 0.5 | 1 | 0.5
B-2 | Schemas and Models | 0.5 | 1 | 1.5
B-3 | User routes and validations | 1 | 1.5 | 1.5
B-4 | User CRUD | 1.5 | 2 | 3
B-5 | Task routes and validations | 0.5 | 1 | 1
B-6 | Task CRUD | 1.5 | 2 | 1
B-7 | Task transition routes and logic | 1 | 2 | 0.5
B-8 | Login routes and logic | 1 | 1.5 | 1
B-9 | Authorization on other routes | 1 | 1.5 | 0.5
B-10 | AI route to get a description | 0.5 | 1 | 0.5
B-11 | OpenAI API integration | 2 | 3 | 0.5
B-12 | Logging middleware | 0.5 | 1 | 1
B-13 | Global exception handling | 1 | 1.5 | 3
B-14 | Seeders for demo data | 1 | 2 | 1.5
B-15 | Code refactoring | 3 | 5 | 5
B-16 | Adding Configuration Files | 1 | 2 | 4 | faces some challenges
Frontend
F-1 | Create a basic template page | 2 | 3 | 1
F-2 | Login page with form and validation | 1.5 | 2 | 0.3
F-3 | login api call and maintain auth | 1 | 2 | 1
F-4 | Task List page | 2 | 4 | 1
F-5 | Task create, edit, and delete UI | 2 | 4 | 1
F-6 | Task create, edit, and delete api call | 2 | 3 | 1
F-7 | Task status update UI and api call | 1 | 2 | 0.5
F-8 | Task description from AI suggestion | 1 | 2 | 1
For Admin
F-9 | User List page | 1 | 1.5
F-10 | User create, edit, and delete UI | 1 | 1.5
F-11 | User create, edit, and delete api call | 1 | 1.5